## Sheet1
Week |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Start: 18-Oct-2016, Week beginning -> | Priority | Resp. | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02
Important Milestones |  |  | 5: Demo-1; 7: Demo-2; 9: UAT- on Clarity Server | UAT on Rack space Server | Go Live
Search
Search database search - 9 sites | 1 | bar: 1 to 6
Live Search - 3 sites
Record Observations | bar: 4
Search Que Engine - to handle Live Search from multiple requests | bar: 7 to 8
Adding Observations based on Manual Search | bar: 5 to 6
Rules for identifying sites - based on Country / Sponsor | 4
Set up on Clarity Server | bar: 4
Modifications based on user feedback | bar: 5 to 6; 8
Reports
Investigator comp Form - PDF
Search History
Login History | 10
Data Extraction History | 10
Modifications based on user feedback | bar: 8
Additional reports
Admin
User | 2
User Role | 2
Password Generation - email | 3
Server Set up
Clarity | bar: 4
RackSpace | bar: 8

## Sheet2
SearchResults (Save Search Results) | Display Name
SearchedBy
SearchStartedOn
SearchClosedOn
ICON Project Number:
Sponsor Protocol No.:
Investigator Name | NameToSearch / Principal Investigator Name
MLNumber | text 100
Address: | text 500
Sub-Investigator Names / ML # (If Applicable)
IssuesIdentified | bool, matches approved.
SitesIncludedInSearch (List)
Site Name
Site URL
SourceDate
SearchMode | enum: Auto - DB / Auto - LIve / Manual
ScannedOn
Matches | text -
MatchedFull | number
MatchedPartial | number
IssueIdentified | bool
One or more records per site.
Issue No. | Integer (for the purpose of reordering the Issue)
VerifiedOn | Date of Inspection / Action
ItemReferenceNumber | Row Number / Page Number etc
ItemReferenceText | Description: Page 3, row 7 etc.
IssueIdentified | bool, Yes for Accepted, No for rejected.
Issues | text -

## Sheet3
No | Item | Priority
General
Application Title incorrect
Input Form
Form Validation
Drag Drop File Upload
Delete Comp Form
Row Styling - clickable
Highlight Selected Row
Retain Selected Row on return
Status: Match Found, Status: Open, Closed
Remove columns: Study, Protocol, Country.
Summary Sheet
No | Item | Priority
Site Name + URL on the same column
Match column: Matches: Full: None, Partial: 5
Status: 5 maches, 0 observations
Closed Status: Open / Closed.
Row Styling: selectable
Detail Form
Pop Up
Status selection
Record Details: improve formatting of text
site link on Site Name title
Header Form: Status: Open / Closed
Order by Issue No.
alt layout: List records marked with Issue Details, pop up checked records to select
Display two lists.
Top list is a form layout
Bottom list is a table
If a item is selected it moves to the top list where observations etc can be added.
When unchecked, it will move to bottom list.

## Actions - Post - Demo1
Demo - 1 | 21-11-2016
Location | ICON-Bangalore
Present | Dinesh - in person
Devendra - remote
Patrick, Divya and Praddep in person
|  | Handled by | Priority | Due | Done
Points identified in the meeting
1 | Ensure all sites are loaded, | Pradeep | 1 | 2016-11-23 | one site to be included.
| Show error message if not loaded |  | 1 | 2016-11-23
| Provide reload option for sites not loaded |  | 1 | 2016-11-23
2 | Combine records from the same audit | Pradeep | 1 | 2016-11-24
3 | Add observation: name combiation searched (permutations used) |  | 3
4 | Comp form with multiple names | Pradeep | 0 |  | Done
| Upload names grouped for a comp form |  |  |  | Done
5 | Record links wherever available | Pradeep | 1 | 2016-11-24
6 | Pdf / image attachment to comp form | Pradeep | 2
7 | SAM site - include in search | Pradeep | 2 | 2016-11-25
8 | Login |  | 3
| User name must be case insensitive | Pradeep |  | 2016-11-28
| Progress - while logging in | Divya |  | 2016-11-28
Remember me - local storage
Open Compliance Form
| Download excel form template |  | 0 |  | Done
| Status Column - with color circle + legend |  | 1
| Filters - load from server |  | 2
| Quick Search Filters |  | 2
| Upload Dialog must close when upload is complerted - provide status etc |  | 1 |  | Priority
| Upload file - validate - display error message |  | 1
Summary section
Compliance Form
| Form Validation - for Study Number etc |  | 2
| Country drop down |  | 2
| disable buttons when Search is in progress |  | 2
Investigator:
| Investigator Validation - min 2 components in name, non alpha chacaters - prevent |  | 2
| get Study Numbers from server |  | 2
| Delete Investigator Dialog confirm + Up , Dn |  | 2
| Enable Search button only when Investigayot / site is added |  | 2
| Investigator Status Column |  | 1
Sites:
| Add Manual Site |  | 0
| Remove Manual Sites |  | 1
Column: Issues identified - retest
Add findings - for site
Findings:
Add Findings - at comp form level
Investigator Summary
Ht of summary site boxes - uniform
Add Findiings - for Investigator
| Findings | Divya
| Correct all links |  | 1 | 2016-11-23
| Show site link |  | 1 | 2016-11-23
| Display links in record details |  | 1 | 2016-11-24
| Select - > Add to Observations |  | 0 | 2016-11-23
Disable 'Add for site …' button when zero records
Search Action
Site Source Date - Save while extracting, overwrite date if exists.
| Was also searched |  | 1
Comp Form Genertation
| Date of Action -> Inspection Date |  | 1
General
| Test Cases | Patrick
Optional Sites - World Health Check - etc. to be added to Search Sites
Routing issues
4 | Country specific rules | Pradeep | 2
7 | Report | Patrick | 3 | 2016-11-28
Report with filters
Filters:
Matched, not matched,
Issues identified, Issues not identified
Name - Name to Search
Name - Searched by
Date of Search - from - to
Admin
User Managemen t
5 | User Creation |  | 2
| Name, Role | Patrick |  | 2016-11-28
6 | Password generation |  | 2
By admin
By user
| set up email |  | 3
2 | show searches according to user | Pradeep | 2 | 2016-11-28
2 | Multiple users upload files - Que system | Pradeep | 2
3 | Mark Site Review completed | Pradeep | 1 | 2016-11-28 | Done
| Roll up - Review completed |  | 0 |  | Done
| Comp Form output | Pradeep
| Word |  | 3 | 2016-11-28 | Done
| PDF |  | 5
Image capture
Site Summary
| Type of Scan: Database / Live / Manual |  |  | 2016-11-28 | Done
1 | Role access, admin, user | Pradeep | 3 | 2016-11-28
| Routing defaults | Divya / Patrick | 3
| Dialog - confirm delete | Divya / Patrick | 3 | 2016-11-23 | Done
Qs to Dinesh - call on 26-Dec-2016
1 | Sponsor based sites - how to find sponsor from available address?
2 | Name To search - want to restrct the name to minimum two parts - One part name produces a large number of results and is difficult to handle.
3 | Can a user modify other user's ICFs
4 | ICFs generated through Upload
a | After the sites are scanned, the name cannot be edited.
Can the Project No, address etc modified?
Can a new name be added
Can an existing name be deleted
Country specific sites will be added automatically, can they be removed later?
In the existing arrangement, the user has to open each site (Findings Page) and mark the site as 'Review Completed"
Findings
Is an Issue
Explanation
Each Observation has a flag, Is an Issue.
Each site in the compliance form has a column 'Issues Identified'. If one or more Investigators under the site has a observation with flag 'Is An Issue' then the site is marked 'Issues Identified'
Q:
Can we automatically add the fully matching records to observations and flag them as 'Is an Issue'
If yes, can the user remove the automatically added record or remove the 'Is an Issue' flag
Record Details: Transfer to findings. Can you provide the content for each site that has to be transferred to findings.
Inspection Date - how to find? For each site
Review
Application needs to know if all the site results for all the investigators are reviewed, hence the flage 'Review completed'
By defulat only my 'Review not completed' forms will be displayed, other forms can be viewed by changing the filters.
Can we provide a facility where the user can mark all sites to 'Review Completed', or conditionally, only for No match found or partiall matched items