## Sheet1
Project plan - Development of ICON Due Diligence Automate System
| By Clarity: |  |  | By Icon:
Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Start: 18-Oct-2016, Week beginning -> | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02
Important Milestones | 2016-11-14: Demo-1; 2016-11-28: Demo-2; 2016-12-12: UAT- on Clarity Server; 2016-12-26: UAT on Rack space Server; 2017-01-02: Go Live
Search functionality
Search database search - 9 sites | bar: 2016-10-17 to 2016-11-21
Live Search - 3 sites | bar: 2016-11-07 to 2016-11-21
Record Observations | bar: 2016-11-07
Search Que Engine - to handle Live Search from multiple requests | bar: 2016-11-28 to 2016-12-05
Adding Observations based on Manual Search | bar: 2016-11-14 to 2016-11-21
Rules for identifying sites - based on Country / Sponsor
Set up on Clarity Server | bar: 2016-11-07
Modifications based on user feedback | bar: 2016-11-14 to 2016-11-21; 2016-12-05
Reports
Investigator comp Form - PDF
Search History
Login History
Data Extraction History
Modifications based on user feedback | bar: 2016-12-05
Additional reports
Admin
User
User Role
Password Generation - email
Server Set up
Clarity | bar: 2016-11-07
RackSpace | bar: 2016-12-05