## Sheet1
Week |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Start: 18-Oct-2016, Week beginning -> | Priority | Resp. | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02
Important Milestones |  |  | 5: Demo-1; 7: Demo-2; 9: UAT- on Clarity Server | UAT on Rack space Server | Go Live
Search
Search database search - 9 sites | 1 | bar: 1 to 6
Live Search - 3 sites
Record Observations | bar: 4
Search Que Engine - to handle Live Search from multiple requests | bar: 7 to 8
Adding Observations based on Manual Search | bar: 5 to 6
Rules for identifying sites - based on Country / Sponsor | 4
Set up on Clarity Server | bar: 4
Modifications based on user feedback | bar: 5 to 6; 8
Reports
Investigator comp Form - PDF
Search History
Login History | 10
Data Extraction History | 10
Modifications based on user feedback | bar: 8
Additional reports
Admin
User | 2
User Role | 2
Password Generation - email | 3
Server Set up
Clarity | bar: 4
RackSpace | bar: 8

## Sheet2
SearchResults (Save Search Results) | Display Name
SearchedBy
SearchStartedOn
SearchClosedOn
ICON Project Number:
Sponsor Protocol No.:
Investigator Name | NameToSearch / Principal Investigator Name
MLNumber | text 100
Address: | text 500
Sub-Investigator Names / ML # (If Applicable)
IssuesIdentified | bool, matches approved.
SitesIncludedInSearch (List)
Site Name
Site URL
SourceDate
SearchMode | enum: Auto - DB / Auto - LIve / Manual
ScannedOn
Matches | text -
MatchedFull | number
MatchedPartial | number
IssueIdentified | bool
One or more records per site.
Issue No. | Integer (for the purpose of reordering the Issue)
VerifiedOn | Date of Inspection / Action
ItemReferenceNumber | Row Number / Page Number etc
ItemReferenceText | Description: Page 3, row 7 etc.
IssueIdentified | bool, Yes for Accepted, No for rejected.
Issues | text -

## Sheet3
No | Item | Priority
General
Application Title incorrect
Input Form
Form Validation
Drag Drop File Upload
Delete Comp Form
Row Styling - clickable
Highlight Selected Row
Retain Selected Row on return
Status: Match Found, Status: Open, Closed
Remove columns: Study, Protocol, Country.
Summary Sheet
No | Item | Priority
Site Name + URL on the same column
Match column: Matches: Full: None, Partial: 5
Status: 5 maches, 0 observations
Closed Status: Open / Closed.
Row Styling: selectable
Detail Form
Pop Up
Status selection
Record Details: improve formatting of text
site link on Site Name title
Header Form: Status: Open / Closed
Order by Issue No.
alt layout: List records marked with Issue Details, pop up checked records to select
Display two lists.
Top list is a form layout
Bottom list is a table
If a item is selected it moves to the top list where observations etc can be added.
When unchecked, it will move to bottom list.

## Actions - Post - Demo1
Demo - 1 | 21-11-2016
Location | ICON-Bangalore
Present | Dinesh - in person
Devendra - remote
Patrick, Divya and Praddep in person
|  | Handled by | Priority | Due | Done
Points identified in the meeting
1 | Ensure all sites are loaded, | Pradeep | 1 | 2016-11-23 | one site to be included.
| Show error message if not loaded |  | 1 | 2016-11-23
| Provide reload option for sites not loaded |  | 1 | 2016-11-23
2 | Combine records from the same audit | Pradeep | 1 | 2016-11-24
3 | Add observation: name combiation searched (permutations used) |  | 3
4 | Comp form with multiple names | Pradeep | 0 |  | Done
| Upload names grouped for a comp form |  |  |  | Done
5 | Record links wherever available | Pradeep | 1 | 2016-11-24
6 | Pdf / image attachment to comp form | Pradeep | 2
7 | SAM site - include in search | Pradeep | 2 | 2016-11-25
8 | Login |  | 3
| User name must be case insensitive | Pradeep |  | 2016-11-28
| Progress - while logging in | Divya |  | 2016-11-28
Remember me - local storage
Open Compliance Form
| Download excel form template |  | 0 |  | Done
| Status Column - with color circle + legend |  | 1
| Filters - load from server |  | 2
| Quick Search Filters |  | 2
| Upload Dialog must close when upload is complerted - provide status etc |  | 1 |  | Priority
| Upload file - validate - display error message |  | 1
Summary section
Compliance Form
| Form Validation - for Study Number etc |  | 2
| Country drop down |  | 2
| disable buttons when Search is in progress |  | 2
Investigator:
| Investigator Validation - min 2 components in name, non alpha chacaters - prevent |  | 2
| get Study Numbers from server |  | 2
| Delete Investigator Dialog confirm + Up , Dn |  | 2
| Enable Search button only when Investigayot / site is added |  | 2
| Investigator Status Column |  | 1
Sites:
| Add Manual Site |  | 0
| Remove Manual Sites |  | 1
Column: Issues identified - retest
Add findings - for site
Findings:
Add Findings - at comp form level
Investigator Summary
Ht of summary site boxes - uniform
Add Findiings - for Investigator
| Findings | Divya
| Correct all links |  | 1 | 2016-11-23
| Show site link |  | 1 | 2016-11-23
| Display links in record details |  | 1 | 2016-11-24
| Select - > Add to Observations |  | 0 | 2016-11-23
Search Action
Site Source Date - Save while extracting, overwrite date if exists.
| Was also searched |  | 1
Comp Form Genertation
| Date of Action -> Inspection Date |  | 1
General
| Test Cases | Patrick
Optional Sites - World Health Check - etc. to be added to Search Sites
Routing issues
4 | Country specific rules | Pradeep | 2
7 | Report | Patrick | 3 | 2016-11-28
Report with filters
Filters:
Matched, not matched,
Issues identified, Issues not identified
Name - Name to Search
Name - Searched by
Date of Search - from - to
Admin
User Managemen t
5 | User Creation |  | 2
| Name, Role | Patrick |  | 2016-11-28
6 | Password generation |  | 2
By admin
By user
| set up email |  | 3
2 | show searches according to user | Pradeep | 2 | 2016-11-28
2 | Multiple users upload files - Que system | Pradeep | 2
3 | Mark Site Review completed | Pradeep | 1 | 2016-11-28 | Done
| Roll up - Review completed |  | 0 |  | Done
| Comp Form output | Pradeep
| Word |  | 3 | 2016-11-28 | Done
| PDF |  | 5
Image capture
Site Summary
| Type of Scan: Database / Live / Manual |  |  | 2016-11-28 | Done
1 | Role access, admin, user | Pradeep | 3 | 2016-11-28
| Routing defaults | Divya / Patrick | 3
| Dialog - confirm delete | Divya / Patrick | 3 | 2016-11-23 | Done