## Sheet1
Start: 18-Oct-2016, Week beginning -> | Priority | Resp. | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19
Search Engine
Search 12 sites - database search | 1 | bar: 2016-10-17 to 2016-10-24
Search Que Engine | bar: 2016-10-31
Live Search - 4 sites | bar: 2016-11-07
Description of findings - transfer content from accepted Item
INVESTIGATOR COMPLIANCE SEARCH FORM
UI
Repository
--
Set up on Clarity Server | bar: 2016-10-24
For Customer Demo |  |  | 2016-10-31: Demo; 2016-11-14: Clarity UAT-1; 2016-11-28: Rackspace - UAT
Reports
Investigator comp Form - PDF | bar: 2016-10-31
Search History
Login History | 10 | bar: 2016-11-07
Data Extraction History | 10 | bar: 2016-11-07
Admin
User | 2 | bar: 2016-10-24
User Role | 2 | bar: 2016-10-24
Password Generation - email | 3
Site Configuration
Countries | 4 | bar: 2016-10-31
Sponsors | 4 | bar: 2016-10-31
Sites - define all sites, auto / manual | 4 | bar: 2016-10-31
Site mapping to Country / Sponsor | 4 | bar: 2016-10-31

## Sheet2
SearchResults (Save Search Results) | Display Name
SearchedBy
SearchStartedOn
SearchClosedOn
ICON Project Number:
Sponsor Protocol No.:
Investigator Name | NameToSearch / Principal Investigator Name
MLNumber | text 100
Address: | text 500
Sub-Investigator Names / ML # (If Applicable)
IssuesIdentified | bool, matches approved.
SitesIncludedInSearch (List)
Site Name
Site URL
SourceDate
SearchMode | enum: Auto - DB / Auto - LIve / Manual
ScannedOn
Matches | text -
MatchedFull | number
MatchedPartial | number
IssueIdentified | bool
One or more records per site.
Issue No. | Integer (for the purpose of reordering the Issue)
VerifiedOn | Date of Inspection / Action
ItemReferenceNumber | Row Number / Page Number etc
ItemReferenceText | Description: Page 3, row 7 etc.
IssueIdentified | bool, Yes for Accepted, No for rejected.
Issues | text -