## Sheet1
Comments
Automatic hide of the web links with no matches are not working right now and instead displays all websites while review. |  | 2
2. Any update on our requirement to include a link in the email for the QCer to access the tool directly. |  | 0
3. When a resource Undo the QC request, can there be an option to ask the reason for cancelling and the same reason be copied in the email as “Dinesh has recalled the review request as this was not meant to send for QC”. |  | 2
4. Currently, the requests under the Quality check page is not sorted proper, can this be sorted out to display the recent one on top so it is easy to access. |  | 1
5. Sub Is (+) option still missing in the Quality Checks to see the list of all Sub Is. |  | 1
6. Please check on the upload & download file options as it didn’t work as expected and sometime adding multiple files doesn’t pick up all. | To be checked
7. For QCer, “Not Applicable” option under the dropdown can be removed as this not relevant. |  | 2
8. The following text needs to be replaced. |  | 1
a. Name of “QC” tab to be renamed as QC Summary.
b. QC Request tab to name as Supporting Documents.
c. In QC tab, the QC Summary be renamed as QC Findings.
d. In QC Tab, the source name be changed to source number.
9. The tabs needs to be rearranged like, QC Summary, Compliance Form & then Supporting Documents. |  | 1
10. The comment option provided in the QC Request & Compliance Form tab is currently allowing only 1 comment to be added and adding any other, replaces the previous ones. So can there be option to the QCer to add multiple comments so that keeps adding up in the summary as they may have different ones per the category. |  |  | 24 | 2018-02-27
11. No action made on this below point yet. So could you please provide us an update on this.
a. Instead of the Fail or Pass in the QC tab, the option to be as “QC Completed – No Issues” & “QC Completed – Issues Noted” (This is just for your reference and please have what was discussed in our meeting with regards to this). |  | 1
12. Once QC is received back, the reviewer is not able to edit the information provided as it remains locked. So the ability to edit the information be provided to the reviewer to make any change to the findings. | Recheck | 2
13. Currently, “Save” button is missed for reviewer while correcting and hence, this prevents the reviewers to record any comment on the comment A & B. Please correct this as needed. | Recheck | 2
14. Once the QC correction is complete, the tool is moving the request to Completed ICSF which is incorrect while this should be moved to Review Completed ICSFs to provide decision back to the reviewer to move to Completed ICSF manually or correct the same if needed. |  | 2
15. Currently, we don’t have any location or report to know what were the comments as well as the correction made on the whole QC workflow. So can the QC summary table be copied in the confirmation email after the QC is complete and similarly, QC correction details be copied in an email which goes back to the QCer to confirm on the action. | We can provide the QC Details in the Compliance Form in a separate tab. This will provide all the information in a central location. Please check and advise. |  | 2 | 2018-02-27
16. Not sure if this below point was considered and requesting your confirmation.
a. Currently, the User is able to see the real time comments being added for any QC in the Quality Checks tab and please prevent the access of real time to the reviewer as they should only be able to view once the QC comments only after the same is complete. | Recheck
17. We have a scenario for which we need to know how this QC workflow will behave and hence, requesting you to have a check on this as well.
a. In most of the cases the spelling of an investigator might be wrongly provided and search completed as well and while the QCer would advise to rerun the search on the correct name. If this scenario is imagined in this workflow, can the reviewer add another investigator to the search on the correct name and remove the old incorrect named PI. Any advice on this case is appreciated. | Yes, Compliance Form can be edited normally by the 'Assigned To' person. To rename an existing Investigator, the user has to remove the current investigator and add a new investigator. The application will carry out the Searches for the new investigator as soon as the Form is Saved.