## Sheet1
Week |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Start: 18-Oct-2016, Week beginning -> | Priority | Resp. | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02
Important Milestones |  |  | 5: Demo-1; 7: Demo-2; 9: UAT- on Clarity Server | UAT on Rack space Server | Go Live
Search
Search database search - 9 sites | 1 | bar: 1 to 6
Live Search - 3 sites
Record Observations | bar: 4
Search Que Engine - to handle Live Search from multiple requests | bar: 7 to 8
Adding Observations based on Manual Search | bar: 5 to 6
Rules for identifying sites - based on Country / Sponsor | 4
Set up on Clarity Server | bar: 4
Modifications based on user feedback | bar: 5 to 6; 8
Reports
Investigator comp Form - PDF
Search History
Login History | 10
Data Extraction History | 10
Modifications based on user feedback | bar: 8
Additional reports
Admin
User | 2
User Role | 2
Password Generation - email | 3
Server Set up
Clarity | bar: 4
RackSpace | bar: 8

## Sheet2
SearchResults (Save Search Results) | Display Name
SearchedBy
SearchStartedOn
SearchClosedOn
ICON Project Number:
Sponsor Protocol No.:
Investigator Name | NameToSearch / Principal Investigator Name
MLNumber | text 100
Address: | text 500
Sub-Investigator Names / ML # (If Applicable)
IssuesIdentified | bool, matches approved.
SitesIncludedInSearch (List)
Site Name
Site URL
SourceDate
SearchMode | enum: Auto - DB / Auto - LIve / Manual
ScannedOn
Matches | text -
MatchedFull | number
MatchedPartial | number
IssueIdentified | bool
One or more records per site.
Issue No. | Integer (for the purpose of reordering the Issue)
VerifiedOn | Date of Inspection / Action
ItemReferenceNumber | Row Number / Page Number etc
ItemReferenceText | Description: Page 3, row 7 etc.
IssueIdentified | bool, Yes for Accepted, No for rejected.
Issues | text -

## Sheet3
No | Item | Priority
General
Application Title incorrect
Input Form
Form Validation
Drag Drop File Upload
Delete Comp Form
Row Styling - clickable
Highlight Selected Row
Retain Selected Row on return
Status: Match Found, Status: Open, Closed
Remove columns: Study, Protocol, Country.
Summary Sheet
No | Item | Priority
Site Name + URL on the same column
Match column: Matches: Full: None, Partial: 5
Status: 5 maches, 0 observations
Closed Status: Open / Closed.
Row Styling: selectable
Detail Form
Pop Up
Status selection
Record Details: improve formatting of text
site link on Site Name title
Header Form: Status: Open / Closed
Order by Issue No.
alt layout: List records marked with Issue Details, pop up checked records to select
Display two lists.
Top list is a form layout
Bottom list is a table
If a item is selected it moves to the top list where observations etc can be added.
When unchecked, it will move to bottom list.

## Actions - Post - Demo1
Demo - 1 | 21-11-2016
Location | ICON-Bangalore
Present | Dinesh - in person
Devendra - remote
Patrick, Divya and Praddep in person
|  | Requested By | Requested on | Request Type | Handled by | Enhancement / Bug | Priority | Due | Done
Role
User | Home
User | Home according to user role | [5 empty] | 0
User | Allow for Actve user only. | [5 empty] | 0
User | Landing Page:  Can the landing page be the “Due Diligence Check” instead of Users? | Dinesh | 2017-01-25 |  | Patrick |  | 0
User | Due Diligence Check
User | Download excel form template | [5 empty] | 0 |  | Done
User | Name of the tab be “Due Diligence Search” instead of check | Dinesh | 2017-01-25 |  | Patrick |  | 0
User | Option like “+” sign be provided in main page next to the principal investigator which would list out all the Sub Investigators who were in the search if expanded. | Dinesh | 2017-01-25 |  | Patrick + Pradeep |  | 0 | 2017-02-01
User | Summary No of Reviews pending: etc. | [5 empty] | 0
User | Status Column - with color circle | [5 empty] | 0
User | Status legend - horizontal |  |  |  | Patrick |  | 0
User | Upload Dialog must close when upload is complerted - provide status etc | [5 empty] | 0 |  | Priority
User | Upload file - validate - display error message |  |  |  | Pradeep |  | 0
User | Pagination |  |  |  | Patrick |  | 0
User | The name of the buttons be just “Manual Search” & “Batch Upload” | Dinesh | 2017-01-25 |  |  |  | 0
User | Name of the “Sample Upload Template” to “Batch Upload Template” | Dinesh | 2017-01-25 |  |  |  | 0
User | Could only the Pending reviews be shown in the main page instead of all? | Dinesh | 2017-01-25 |  | Patrick + Pradeep |  | 0
| Extractin Pending Status, include errors while extracting | [5 empty] | 0
User | Compliance Form
User | Form Validation - for Study Number etc | [5 empty] | 0
User | Status Circle for page | [5 empty] | 0
User | Activity Indicator at all levels - Saving, loading | [5 empty] | 2
User | Country drop down | [5 empty] | 9
User | deactivate guard | [5 empty] | 2
User | get Study Numbers from server | [5 empty] | 9
| Clicking 'Add Investigator' from tabs does not open Investigator Tab |  |  |  |  | Bug | 0
| Changes in input fields according to Input Excel File | ICON | 2017-03-24 |  |  |  | 1
User | Investigator:
User | Investigator Validation - min 2 components in name, non alpha chacaters - prevent | [5 empty] | 2
User | Delete Investigator Dialog confirm + Up , Dn | [5 empty] | 0
User | Investigator Status Column | [5 empty] | 0
User | Investigator Id | [5 empty] | 0
User | Status Circle | [5 empty] | 0
User | Inspection Date revised logic | Dinesh | 2017-01-25 |  | Pradeep |  | 0
User | v In the search, could an option be provided to change the Role of the investigator, if needed? | Dinesh | 2017-01-25 |  | Patrick | ?? | 0
| Does not retain page number after returning from Finding |  |  |  |  | Bug | 2
| Do not Save Investigator if name is blank |  |  |  |  | Bug | 0
User | Sites:
User | Add Manual Site | [5 empty] | 0
User | Remove Manual Sites | [5 empty] | 0
User | Add findings - for site | [5 empty] | 0
User | Additional sites in separate section | [5 empty] | 0
| Additional Sites - web link is not shown |  |  |  |  | Bug | 0
| Column: Last Updated |  |  |  |  | Enhancement | 0
User | Findings:
User | Add Findings - at comp form level | [5 empty] | 0
User | Site Source Date - display. | [5 empty] | 0
User | v Please interchange the 7th and 8th Web links in all. | Dinesh | 2017-01-25 |  | Pradeep |  | 0
User | v Worldcheck should be the default 13th web link and this should have provision to provide the descriptions of findings if found manually. | Dinesh | 2017-01-25 |  | Pradeep |  | 0
| Mark all manual sites ReviewCompleted = true by default. | Devendra | 2017-03-23 | Webex | Patrick |  | 0
User | Investigator Summary
User | Ht of summary site boxes - uniform | [5 empty] | 0
User | Status Circle for page | [5 empty] | 9
User | Add Findiings - for Investigator | [5 empty] | 9
User | Status Circle Column | [5 empty] | 0
User | Review Pending status: Yes / No | [5 empty] | 0
User | Mark currently selected item | [5 empty] | 0
| Focus on currently selected item button - so that the page scrolls and displays the currently selected item. | [5 empty] | 9
User | Investigator Summary Page Review status can be marked as Review Completed for DB/Live sites where no match is found. This value can be changed by the user if required. | Devendra/Dinesh | 2017-02-09 |  |  |  | 0
User | Investigator Summary Page, Summary. Add items: Data Extraction Errors and Review Pending | Devendra/Dinesh | 2017-02-09 |  |  |  | 0
User | Investigator Summary Page, Provide filters such as 'Review Pending', 'Matches Found' etc. | Devendra/Dinesh | 2017-02-09 |  |  |  | 0
User | Findings
User | Correct all links | [5 empty] | 0 | 2016-11-23
User | Show site link | [5 empty] | 0 | 2016-11-23
User | Display links in record details | [5 empty] | 0 | 2016-11-24
User | Select - > Add to Observations | [5 empty] | 0 | 2016-11-23
User | Disable 'Add for site …' button when zero records | [5 empty] | 0
User | hide 'Add for site' for manual sites | [5 empty] | 0
User | links | [5 empty] | 0
User | attachments |  |  |  | Pradeep |  | 3
User | copy record details to observations - button |  |  |  | Pradeep |  | 3
User | Match Weightage in dialog full / partial |  |  |  | Pradeep / Patrick |  | 3
User | deactivate guard |  |  |  | Patrick |  | 0
User | Combine records for same audit | [5 empty] | 0
User | Findings Page 'Add from site's matching records' change text to 'Review Matching Records' | Devendra/Dinesh | 2017-02-09 |  |  |  | 0
User | Findings Page, 'Add' change text to 'Add Additional Findings'. | Devendra/Dinesh | 2017-02-09 |  |  |  | 0
User | Findings Page. Summary: Provide hyper-links on 'Full Match' and 'Partial Match' so that if the user clicks on the hyper link the application opens the list of Full or Partial match records. | Devendra/Dinesh | 2017-02-09 |  |  |  | 0
User | List of Specially … Page Number: 0, Matches > Number of Name components |  |  |  | Pradeep | Bug | 0
| DateOfInspection - lable for DB/Live Site | Clarity/ check with ICON | 2017-03-24 |  | Patrick | Enhanement | 0
| DateOfInspection - Date picker for Manual Sites | Clarity/ check with ICON | 2017-03-24 |  | Patrick | Enhanement | 0
| Is An Issue - set default true - reason: Findings is always / most of the time is an Issue. | Clarity/ check with ICON |  |  |  | Enhanement | 0
Save
| Status Color displays grey immediately on first Save. |  |  |  |  | Bug | 1
User | ALL Searches
User | View all ICFs | [5 empty] | 0
User | v All ICSFs tab be changed to “All Searches”. | Dinesh | 2017-01-25 |  |  |  | 0
User | Filters + No match found, Review pending | [5 empty] | 3
User | Generate ICF button | [5 empty] | 0
| Column Active - replace with Review Completed |  |  |  |  | Change | 0
| Column Searched On and Assigned to are interchanged. |  |  |  |  | Bug | 0
User | Closed ICFs
User | List | [5 empty] | 0
User | Closed ICSFs tab be changed to “Closed Reviews”. | Dinesh | 2017-01-25 |  |  |  | 0
User | Filters
User | Move to Open ICFs | [5 empty] | 0
User | Manage ICSFs tab be changed to “Manage Reassignments” | Dinesh | 2017-01-25 |  |  |  | 0
Sim. To ALL ICFs
Project Number
Protocol Number
User | Components
User | Generate Comp Form component | [5 empty] | 0
User | Status Circule Legend - Horizontal | [5 empty] | 0
User | Confirm Dialog | [5 empty] | 2
User | Date Picker | [5 empty] | 0
User | Pagination | [5 empty] | 0
User | General
User | Please have the Legends in all pages for better clarity. | Dinesh | 2017-01-25 |  | Patrick |  | 0
User | Can we move the Role & Account to top left Corner with option coming up while clicked on name. | Dinesh | 2017-01-25 |  | Patrick |  | 0
| Activity Indicator for all listing pages |  |  |  |  | Enhanement | 3
User | Test Cases |  |  |  | Patrick |  | 0
User | Optional Sites - World Health Check - etc. to be added to Search Sites | [5 empty] | 0
User | Routing issues | [5 empty] | 9
User | Country specificsite rules |  |  |  | Pradeep |  | 0
| Sponsor specific site rules | [5 empty] | 0
User | Report - Output Report |  | 2017-03-24 |  | Patrick |  | 1 | 2016-11-28
User | Report with filters | [5 empty] | 0
User | Filters:
User | Matched, not matched,
User | Issues identified, Issues not identified
User | Name - Name to Search
User | Name - Searched by
User | Date of Search - from - to
User | Menu
User | Logged in User, role css | [5 empty] | 0
User | items spacing bring closer | [5 empty] | 0
User | Version Number | [5 empty] | 0
| Devp / Staging / - flag under ICON flag | [5 empty] | 0
User | Compliance Form Generation
User | Enable Compliance Form generation only if the Review is completed. | Devendra/Dinesh | 2017-02-09 |  |  |  | 0
User | Last updated on on footer. | [5 empty] | 0
User | The current excel file format will be changed to handle recording Investigators, one per row. | Devendra/Dinesh | 2017-02-09 |  |  |  | 0
User | PDF | [5 empty] | 3
User | embed attachments, pdf etc
User | Date of Action -> Inspection Date | [5 empty] | 0
User | Logged in User
User | Login Details
User | Filter: From, To | [5 empty] | 0
User | Test for Login failed | [5 empty] | 0
| IP Address Column | [5 empty] | 0
Admin | Admin
Admin | Dashboard
Admin | Live Scan Status - On/Off, Que Status | [5 empty] | 0
Admin | Site Configuration
| Site List, Add, Edit, Delete, ExcludeSI | Dinesh | 2017-03-15 |  |  |  | 0
| Country Specific sites | Dinesh | 2017-03-15 |  |  |  | 0
| Sponsor specific site rules |  | 2017-03-15 |  |  |  | 0
Admin | Manage Compliance Forms
Admin | Filters | [5 empty] | 0
Admin | Date Picker | [5 empty] | 0
Admin | Delete | [5 empty] | 0
Admin | Generate Comp Form component | [5 empty] | 0
Admin | Manage ICFS - Reassign, Delete | [5 empty] | 0
Filters
| Assigned to | [5 empty] | 2
Admin | User Management
Admin | User Creation | [5 empty] | 0
Admin | Name, Role, Email Id |  |  |  | Patrick |  | 0 | 2016-11-28
Admin | Edit field validations, name - no space, email id. | [5 empty] | 0
Admin | New user: Active by default. |  |  |  |  | Patrick | 0
Admin | Password generation | [5 empty] | 0
Admin | Password reset - message must include name of user |  |  |  |  | Patrick | 2
Admin | Deletion of user - check referential records |  |  |  |  | Patrick | 2
Admin | Logged in user should not modify self record |  |  |  |  | Patrick | 0
Admin | set up email | [5 empty] | 0
Admin | Pagination | [5 empty] | 0
Admin | show searches according to user |  |  |  | Pradeep |  | 0 | 2016-11-28
| User Name - check for unique | [5 empty] | 2
| User Full Name | [5 empty] | 1
Admin | Login Details |  |  |  | Pradeep
Admin | Filters: By User Name | [5 empty] | 1
Admin | Column: IP Address | [5 empty] | 0
Admin | Logout - info
Admin | Error Log |  |  |  | Pradeep |  | 2
Admin | Change TextLog to DBLog | [5 empty] | 2
Admin | Live Scan Log / Que
Admin | Data Extractor Log
Admin | Others
Admin | Data Dump |  |  |  | Pradeep |  | 3
App Admin | AppAdmin
App Admin | App Admin Role | [5 empty] | 3
App Admin | Start / Stop Application | [5 empty] | 3
App Admin | Schedule Start / Stop | [5 empty] | 3
App Admin | Email to Admins - on repeated errors. | [5 empty] | 3
App Admin | Clear Error Screen Shots | [5 empty] | 0
App Admin | Delete Confirm Error Image | [5 empty] | 2
App Admin | Clear uploaded files | [5 empty] | 3
App Admin | Clear generated Comp Forms | [5 empty] | 3
App Admin | Disk Space | [5 empty] | 3
Download mongo db log
Server Disk free disk space
Mongo service - running status
Mongo Service - stop / start
Background Processes
Excel File Upload
| Store both original file name and generated file name in comp form. | [5 empty] | 0
Live Scan | Live Scan
Live Scan | Multiple users upload files - Que system |  |  |  | Pradeep |  | 0
Live Scan | Windows Service | [5 empty] | 9 |  | Did not work as a windows Service, decided to use console app.
| Console App | [5 empty] | 0
Live Scan | Stop / Start Service | [5 empty] | 0
Live Scan | View Scan History | [5 empty] | 0
Live Scan | Roll up - Review completed | [5 empty] | 0 |  | Done
| Stop Live Scan after n errors | [5 empty] | 2
Data Extractor | Data Extractor
Data Extractor | Set up Task Scheduler on Server | [5 empty] | 0
Data Extractor | Word |  |  |  | Pradeep |  | 0 | 2016-11-28 | Done
Data Extractor | Type of Scan: Database / Live / Manual | [5 empty] | 0 | 2016-11-28 | Done
Data Extractor | Role access, admin, user |  |  |  | Pradeep |  | 0 | 2016-11-28
Data Extractor | Routing defaults |  |  |  | Divya / Patrick |  | 0
Data Extractor | Dialog - confirm delete |  |  |  | Divya / Patrick |  | 0 | 2016-11-23 | Done
Data Extractor | View Scan History | [5 empty] | 0
| handling changes in web site | [5 empty] | 9
General
| About us | [5 empty] | 2
| General: ICON will provide content for the About page. | Devendra/Dinesh | 2017-02-09 |  |  |  | 2
| User Manual / Help | [5 empty] | 2
| Alternate layout for Compliance Form suggested by Clarity. Instead of the current vertical format, Clarity will provide a tab based format. | Clarity / Devendra | 2017-02-09 |  |  |  | 0
| Clarity Logo | [5 empty] | 1
MongDB
| Indexing | [5 empty] | 1
| Backup | [5 empty] | 3
| Restore | [5 empty] | 3
Indexes
| rotate mongo db log | [5 empty] | 2
| Stop/Start/Restart Mongodb Service | [5 empty] | 2
| read list of files in log folder | [5 empty] | 2
| Export / Import collections | [5 empty] | 2
Qs to Dinesh - call on 26-Dec-2016
1 | Sponsor based sites - how to find sponsor from available address? |  |  |  | Dinesh will provide the list of Sponsor which is first 4 letters of the ICON Project number
2 | Name To search - want to restrct the name to minimum two parts - One part name produces a large number of results and is difficult to handle. |  |  |  | Can restrict name to min two components
3 | Can a user modify other user's ICFs |  |  |  | No, can be reassigned.
4 | ICFs generated through Upload
a | After the sites are scanned, the name cannot be edited. |  |  |  | Yes
| Can the Project No, address etc modified? |  |  |  | Yes
| Can a new name be added |  |  |  | Yes
| Can an existing name be deleted |  |  |  | Yes
| Country specific sites will be added automatically, can they be removed later? |  |  |  | yes
| In the existing arrangement, the user has to open each site (Findings Page) and mark the site as 'Review Completed" |  |  |  | No, invividually closed
Findings
| Is an Issue |  |  |  | Explained
Explanation
Each Observation has a flag, Is an Issue.
Each site in the compliance form has a column 'Issues Identified'. If one or more Investigators under the site has a observation with flag 'Is An Issue' then the site is marked 'Issues Identified'
Q:
| Can we automatically add the fully matching records to observations and flag them as 'Is an Issue' |  |  |  | No,
If yes, can the user remove the automatically added record or remove the 'Is an Issue' flag
| Record Details: Transfer to findings. Can you provide the content for each site that has to be transferred to findings. |  |  |  | Dinesh will provide the details
| Inspection Date - how to find? For each site |  |  |  | Dinesh will provide the details
Review
| Application needs to know if all the site results for all the investigators are reviewed, hence the flage 'Review completed' |  |  |  | Explained
| By defulat only my 'Review not completed' forms will be displayed, other forms can be viewed by changing the filters. |  |  |  | Explained
Can we provide a facility where the user can mark all sites to 'Review Completed', or conditionally, only for No match found or partiall matched items
New Pts in the call
1 | Provide an option to re-assign a compliance form | [5 empty] | 0
2 | Compliance Form Layout
| Additional sites to be displayed in a seaparate table | [5 empty] | 2
| Sr Nos for these additional tables will be running from previous table | [5 empty] | 2
| Form footer - to display last updated date | [5 empty] | 3
| Icon Project No and Sponsor Protocal on the same row, Institute and Addres on the second row | [5 empty] | 0
| Investigator Id | [5 empty] | 0
| Menu _> Compliance Form -> Due Deligence Check |  |  |  | Due Diligence Check |  | 0 | Done
| Create > Due Deligence Check (Manual) |  |  |  | Due Diligence Check (Manual) |  | 0 | Done
| Upload .. Due Deligence Check (Upload) |  |  |  | Due Diligence Check (Upload) |  | 0 | Done
| Download Compliance Form -> Sample Upload Template, different location. | [5 empty] | 0 | Done
| Buttons larger | [5 empty] | 0 | Done
| Filters, below action buttons. | [5 empty] | 0 | Done
Bugs