## Sheet1
Week |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Start: 18-Oct-2016, Week beginning -> | Priority | Resp. | 2016-10-17 | 2016-10-24 | 2016-10-31 | 2016-11-07 | 2016-11-14 | 2016-11-21 | 2016-11-28 | 2016-12-05 | 2016-12-12 | 2016-12-19 | 2016-12-26 | 2017-01-02
Important Milestones |  |  | 5: Demo-1; 7: Demo-2; 9: UAT- on Clarity Server | UAT on Rack space Server | Go Live
Search
Search database search - 9 sites | 1 | bar: 1 to 6
Live Search - 3 sites
Record Observations | bar: 4
Search Que Engine - to handle Live Search from multiple requests | bar: 7 to 8
Adding Observations based on Manual Search | bar: 5 to 6
Rules for identifying sites - based on Country / Sponsor | 4
Set up on Clarity Server | bar: 4
Modifications based on user feedback | bar: 5 to 6; 8
Reports
Investigator comp Form - PDF
Search History
Login History | 10
Data Extraction History | 10
Modifications based on user feedback | bar: 8
Additional reports
Admin
User | 2
User Role | 2
Password Generation - email | 3
Server Set up
Clarity | bar: 4
RackSpace | bar: 8

## Sheet2
SearchResults (Save Search Results) | Display Name
SearchedBy
SearchStartedOn
SearchClosedOn
ICON Project Number:
Sponsor Protocol No.:
Investigator Name | NameToSearch / Principal Investigator Name
MLNumber | text 100
Address: | text 500
Sub-Investigator Names / ML # (If Applicable)
IssuesIdentified | bool, matches approved.
SitesIncludedInSearch (List)
Site Name
Site URL
SourceDate
SearchMode | enum: Auto - DB / Auto - LIve / Manual
ScannedOn
Matches | text -
MatchedFull | number
MatchedPartial | number
IssueIdentified | bool
One or more records per site.
Issue No. | Integer (for the purpose of reordering the Issue)
VerifiedOn | Date of Inspection / Action
ItemReferenceNumber | Row Number / Page Number etc
ItemReferenceText | Description: Page 3, row 7 etc.
IssueIdentified | bool, Yes for Accepted, No for rejected.
Issues | text -

## Sheet3
No | Item | Priority
General
Application Title incorrect
Input Form
Form Validation
Drag Drop File Upload
Delete Comp Form
Row Styling - clickable
Highlight Selected Row
Retain Selected Row on return
Status: Match Found, Status: Open, Closed
Remove columns: Study, Protocol, Country.
Summary Sheet
No | Item | Priority
Site Name + URL on the same column
Match column: Matches: Full: None, Partial: 5
Status: 5 maches, 0 observations
Closed Status: Open / Closed.
Row Styling: selectable
Detail Form
Pop Up
Status selection
Record Details: improve formatting of text
site link on Site Name title
Header Form: Status: Open / Closed
Order by Issue No.
alt layout: List records marked with Issue Details, pop up checked records to select
Display two lists.
Top list is a form layout
Bottom list is a table
If a item is selected it moves to the top list where observations etc can be added.
When unchecked, it will move to bottom list.

## Actions - Post - Demo1
Demo - 1 | 21-11-2016
Location | ICON-Bangalore
Present | Dinesh - in person
Devendra - remote
Patrick, Divya and Praddep in person
|  | Handled by | Priority | Due | Done
Points identified in the meeting
1 | Ensure all sites are loaded, | Pradeep | 0 | 2016-11-23 | one site to be included.
| Show error message if not loaded |  | 2 | 2016-11-23
| Provide reload option for sites not loaded |  | 2 | 2016-11-23
2 | Combine records from the same audit | Pradeep | 0 | 2016-11-24
3 | Add observation: name combiation searched (permutations used) | Pradeep | 9
4 | Comp form with multiple names | Pradeep | 0 |  | Done
| Upload names grouped for a comp form |  | 0 |  | Done
5 | Record links wherever available | Pradeep | 0 | 2016-11-24
6 | Pdf / image attachment to comp form | Pradeep | 2
7 | SAM site - include in search | Pradeep | 0 | 2016-11-25
8 | Login
| User name must be case insensitive | Pradeep | 0 | 2016-11-28
| Progress - while logging in | Divya | 0 | 2016-11-28
| Remember me - local storage |  | 0
| Forgot Password |  | 9
| Does not clear previous login - unless browser is closed |  | 0
| Logout - Prod mode: After logout , does not display login page | bug | 0
User
Home
| Home according to user role |  | 0
| Allow for Actve user only. |  | 3
Open Compliance Form
| Download excel form template |  | 0 |  | Done
| Status Column - with color circle + legend |  | 2
| Filters - load from server |  | 2
| Quick Search Filters |  | 2
| Upload Dialog must close when upload is complerted - provide status etc |  | 0 |  | Priority
| Upload file - validate - display error message |  | 2
| Summary section |  | 2
| Pagination |  | 2
Compliance Form
| Form Validation - for Study Number etc |  | 1
| Country drop down |  | 1
| disable buttons when Search is in progress |  | 1
| deactivate guard |  | 1
Investigator:
| Investigator Validation - min 2 components in name, non alpha chacaters - prevent |  | 1
| get Study Numbers from server |  | 2
| Delete Investigator Dialog confirm + Up , Dn |  | 3
| Enable Search button only when Investigayot / site is added |  | 2
| Investigator Status Column |  | 0
| Investigator Id |  | 1
| Status Circle |  | 2
| Close Comp Form only when all reviews are completed |  | 1
Sites:
| Add Manual Site |  | 0
| Remove Manual Sites |  | 0
| Column: Issues identified - retest |  | 1
| Add findings - for site |  | 2
| Additional sites in separate section |  | 1
| Findings: |  | -
| Add Findings - at comp form level |  | 2
Investigator Summary
| Ht of summary site boxes - uniform |  | 0
| Add Findiings - for Investigator |  | 1
| Status Circle |  | 0
| Review Pending status: Yes / No |  | 1
| Findings |  | 2
| Correct all links |  | 0 | 2016-11-23
| Show site link |  | 0 | 2016-11-23
| Display links in record details |  | 0 | 2016-11-24
| Select - > Add to Observations |  | 0 | 2016-11-23
| Disable 'Add for site …' button when zero records |  | 0
| hide 'Add for site' for manual sites |  | 0
| links |  | 0
| attachments |  | 2
| copy record details to observations - button |  | 2
| Match Weightage in dialog |  | 1
| deactivate guard |  | 2
Search Action
| Site Source Date - Save while extracting, overwrite date if exists. |  | 2
| Was also searched |  | 9
| Search Que |  | 2
Comp Form Genertation
| Date of Action -> Inspection Date |  | 2
| Report |  | 1
| View all ICFs |  | 1
| Filters |  | 1
| Generate ICF button |  | 0
| Due Diligence Check |  | 0
| Close ICFs |  | 0
| Summary No of Reviews pending: etc. |  | 2
| Closed ICFs |  | 1
| List |  | 0
| Filters |  | 1
| Move to Open ICFs |  | 0
Compoents
| Generate Comp Form component |  | 0
Status Circule Legend - Horizontal
General
| Test Cases | Patrick | 3
| Optional Sites - World Health Check - etc. to be added to Search Sites |  | 0
| Routing issues |  | 3
4 | Country specific rules | Pradeep | 2
7 | Report | Patrick | 3 | 2016-11-28
| Report with filters |  | 3
Filters:
Matched, not matched,
Issues identified, Issues not identified
Name - Name to Search
Name - Searched by
Date of Search - from - to
Menu
| Logged in User, role css |  | 0
| items spacing bring closer |  | 0
Version Number
Admin
Manage Compliance Forms
Filters
Date Picker
Delete
Generate Comp Form component
User Managemen t
5 | User Creation |  | 0
| Name, Role, Email Id | Patrick | 0 | 2016-11-28
Edit field validations, name, email id.
New user: Active by default.
6 | Password generation |  | 0
Password reset - message must include name of user
Deletion of user - check referential records
By admin
Logged in user should not modify self record
By user
| set up email |  | 0
Pagination
Data Dump
| ICF Management |  | 1
| Manage ICFS - Reassign, Delete |  | 1
2 | show searches according to user | Pradeep | 0 | 2016-11-28
Search Engine
2 | Multiple users upload files - Que system | Pradeep | 1
3 | Mark Site Review completed | Pradeep | 1 | 2016-11-28 | Done
View Scan History
| Roll up - Review completed |  | 1 |  | Done
handling errors
| handling changes in web site |  | 2
| Comp Form output | Pradeep
| Word | Pradeep | 0 | 2016-11-28 | Done
| PDF | Pradeep | 5
| Image capture |  | 3
Site Summary
| Type of Scan: Database / Live / Manual |  | 0 | 2016-11-28 | Done
1 | Role access, admin, user | Pradeep | 0 | 2016-11-28
| Routing defaults | Divya / Patrick | 0
| Dialog - confirm delete | Divya / Patrick | 0 | 2016-11-23 | Done
Qs to Dinesh - call on 26-Dec-2016
1 | Sponsor based sites - how to find sponsor from available address? | Dinesh will provide the list of Sponsor which is first 4 letters of the ICON Project number
2 | Name To search - want to restrct the name to minimum two parts - One part name produces a large number of results and is difficult to handle. | Can restrict name to min two components
3 | Can a user modify other user's ICFs | No, can be reassigned.
4 | ICFs generated through Upload
a | After the sites are scanned, the name cannot be edited. | Yes
| Can the Project No, address etc modified? | Yes
| Can a new name be added | Yes
| Can an existing name be deleted | Yes
| Country specific sites will be added automatically, can they be removed later? | yes
| In the existing arrangement, the user has to open each site (Findings Page) and mark the site as 'Review Completed" | No, invividually closed
Findings
| Is an Issue | Explained
Explanation
Each Observation has a flag, Is an Issue.
Each site in the compliance form has a column 'Issues Identified'. If one or more Investigators under the site has a observation with flag 'Is An Issue' then the site is marked 'Issues Identified'
Q:
| Can we automatically add the fully matching records to observations and flag them as 'Is an Issue' | No,
If yes, can the user remove the automatically added record or remove the 'Is an Issue' flag
| Record Details: Transfer to findings. Can you provide the content for each site that has to be transferred to findings. | Dinesh will provide the details
| Inspection Date - how to find? For each site | Dinesh will provide the details
Review
| Application needs to know if all the site results for all the investigators are reviewed, hence the flage 'Review completed' | Explained
| By defulat only my 'Review not completed' forms will be displayed, other forms can be viewed by changing the filters. | Explained
Can we provide a facility where the user can mark all sites to 'Review Completed', or conditionally, only for No match found or partiall matched items
New Pts in the call
1 | Provide an option to re-assign a compliance form |  | 0
2 | Compliance Form Layout
| Additional sites to be displayed in a seaparate table |  | 2
| Sr Nos for these additional tables will be running from previous table |  | 2
| Form footer - to display last updated date |  | 3
| Icon Project No and Sponsor Protocal on the same row, Institute and Addres on the second row |  | 0
| Investigator Id |  | 0
| Menu _> Compliance Form -> Due Deligence Check | Due Diligence Check | 0 | Done
| Create > Due Deligence Check (Manual) | Due Diligence Check (Manual) | 0 | Done
| Upload .. Due Deligence Check (Upload) | Due Diligence Check (Upload) | 0 | Done
| Download Compliance Form -> Sample Upload Template, different location. |  | 0 | Done
| Buttons larger |  | 0 | Done
| Filters, below action buttons. |  | 0 | Done
Bugs